## Slide 1
www.geant.org
Gyöngyi Horváth (GÉANT)
13 October 2020
GÉANT Innovation-hub

## Slide 2: Why a GÉANT innovation-hub?
GÉANT’s motivation:
Research and Education evolving continuously and for NRENs it is important to identify partners who can help accelerate and expand the innovation ideas to support the technological evolution.
Notes: 2020

## Slide 3: How could an innovation partnership work?
Call
Review
Develop
Report
January (M1)
March (M3)
April (M4) – May (M5)
June (M6) – July (M7)

## Slide 4: Step 1: Call
Call
GÉANT issue a call for participation open to eligible NRENs and any other partners they approve.
The call asks for people to partner on delivering against a specific set of ideas in return for up to 30k for 6 months.
Requirements:
General eligibility criteria
Financial eligibility

## Slide 5: Step 2: Review
Review
All responses are submitted online (need to decide open or closed).
A group of GÉANT community experts review all submissions and decide which should proceed.
Winning teams notified.
Requirements:
Review process
GÉANT Community expert hub reviewers

## Slide 6: Step 3: Development monitoring
Develop
Teams work provide oversight and progress report to GÉANT for 6 months.
Teams should work in 2 week sprints.
Regular public updates on progress.
Requirements:
Reviewers of progress

## Slide 7: Step 4: Report and continuation
Report
All teams attend a showcase to demonstrate work.
Most promising projects continued if necessary.
GÉANT will then review the programme to see if we want to run it again.
Requirements:
Demonstration method
Review panel
Financial plan
General product / service management

## Slide 8: Criteria for projects
Must focus on product development not on research or advocacy or advice and guidance
Must deliver a working product within 6 months
Must be run using an agile approach
Must align with existing work in the area
Must commit to working in the way we define and to joining a showcase at the end of the programme
Notes: 2020

## Slide 9: Issues to address
Mechanism for allocating funding (grant/procurement)
Agreement between GÉANT and project proposers
Contract defined by above and addressing commercial exploitation and IP
Marketing
Eligibility
Submission mechanism (open or closed)
Detailed enough descriptions of work to enable bidders to ensure their proposals align
Notes: 2020

## Slide 10: Example scopes of topics for area of education
Sticky campus
Intelligent campus
Curriculum analytics
Wellbeing analytics
Managing the data estate
Next generation digital learning environment
Working with edtech start-ups
Digital capability
Research data management
Libraries and AI
We would be open to ideas that do not strictly fit these categories as long as they are related. However, these categories will be the priority.
Notes: 2020