## Tabelle1
Stage | Action | status | Owner | % complete | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan
Preparation | Fedor to collect pricing of fibre for 3, 5, 7, 10 years on the north and south routes | Done | Fedor | 100%
Preparation | Matthew G. to use fibre provider RFQ to estimate the cost GEANT part of the build, should include: fibre, amplifiers, installation, support. | Done | Matthew | 100%
Preparation | Create a SIG-TFN and prepare first meeting | Done | Richard/Nadelina | 100%
Preparation | IRU 5-year, 10-year vs lease cost analysis. Understand trade-off between cashflow vs. sustainability. | due Oct 2024 | Matthew | 50% | bar: Aug to Oct
Preparation | Document the operational and support model for T/F | due May 2024 | Guy/Akil/Nial | 0% | bar: Jan to Jun
Pathfinder | Procure fibre PTB-Polish border | Done | Fedor | 100%
Pathfinder | Install bi-directional amplifers on the PTB-PSNC | Done | PSNC | 100%
Pathfinder | System validation and test report | Nov 2024 | PSNC | 0% | bar: Sept to Nov
Pathfinder | Demonstrate TimeMap management of the pathfinder | Nov 2024 | PSNC/WP6 | 50% | bar: Aug to Nov
Pathfinder | Based on pathfinder, develop a support model, identify who is responsible for which part? Integrator, GEANT, NREN, NMI | Dec 2024 | Guy/Akil | 0% | bar: Sept to Dec
Design | SIG-TFN WG to agree high-level technical design for the North route | Nov 2024 | SIG WG | 30% | bar: Sept to Nov
Design | GEANT to create technical design of GEANT fibre links | Nov 2024 | Guy | 30% | bar: Sept to Nov
Design | GEANT to specify bi-directional amps and associate hardware and software requirements. | Nov 2024 | Guy/ SIG WG | 30% | bar: Sept to Nov
Design | Get agreement on the GEANT wavelength plan | Nov 2024 | Guy/ SIG WG | 10% | bar: Sept to Nov
Design | Prepare an FRD for the equipment ITT | Nov 2024 | Guy | 0% | bar: Sept to Nov
contracts | draft an interconnect agreement between GEANT and the NMI/NREN involved | Dec 2024 | Guy/Richard | 50% | bar: Aug to Dec
contracts | Get Revimeve, OB, SURF, PTB, PSNC to sign interconnect agreement | May 2024 | Guy/Richard | 0% | bar: Oct to May
Review and gate | Finance and the PMO to review Matthew's costings and financial model. And advise on a preferred option | Nov 2024 | Alex/Tryfon | 0%
Review and gate | Network Operations team to review and approve the technical design for the Lille-Braunschweig system | Dec 2024 | Guy/Bram/Toby | 0%
Review and gate | Exec to give go-ahead for procurement to begin on the northern route | Dec 2024 | Exec | 0%
North DF Procurement | Prepare ITT for Dark fibre | Dec 2024 | Fedor | 0% | bar: Oct to Dec
North DF Procurement | Dark Fibre ITT launch | Jan 2025 | Fedor
North DF Procurement | Dark fibre review tenders and award | April 2025 | Guy/Fedor | 0% | bar: Feb to Apr
North DF Procurement | Target fibre handover date | Sept 2025 | Fibre provider | 0%
Equip Procurement | Prepare ITT for optical bi-directional amplifiers | Dec 2024 | Guy/Fedor | 50% | bar: Nov to Jan
Equip Procurement | Optical bi-directional amplifiers ITT launch | Feb 2025 | Fedor
Equip Procurement | Optical bi-directional amplifiers review tenders and award | May 2025 | Guy/Fedor | bar: Mar to May
Equip Procurement | Manufacturing lead time for the northern route | Sept 2025 | Fibre provider | 0% | bar: Jun to Sept
Equip Procurement | Target optical bi-directional amplifiers installation completion date | Dec 2025 | Fibre provider | 0% | bar: Oct to Dec
Equip Procurement | Manufacturing lead time for the southern route | Sept 2025 | Fibre provider | 0% | bar: Jan
Equip Procurement | Target optical bi-directional amplifiers installation completion date | Dec 2025 | Fibre provider | 0%
Services design | flywheel preparation
Services design | service turn up
Services design | data repostiory
Services design | system calibration
Services design | design a calibration procedure